## USER
# | Username | Password | Role
1 | Prime | 12345 | Admin
2 | Jack | 12345 | Warehouse
3
4
5
6
7

## Marco
# | Menu | SubMenu | Activity | Status | Notes
1 | Auth | Login | Manage user login (CREATE) | 100% | OK
2 | Admin | Dashboard |  | 100% | Belum tau mau diisi dengan apa
3 | Admin | Manage User | Manage User '(CRUD)' | 100%
4 | Admin | Manage Role | Manage Role '(CRUD)' | 10% | Baru hanya UI
5 | Admin | Manage Menu | Manage Menu '(CRUD)' | 100% | OK
6 | Admin | Manage SubMenu | Manage SubMenu '(CRUD)' | 100% | OK
7 | Admin | Manage Storage | Manage Storage '(CRUD)' | 0%
8 | Production | Material Request | Material Request '(CRUD)' | 20% | Baru hanya UI, Logic
9 | Production | Kitting | Kitting '(CRUD)' | 0%
10 | Production | Kanban Box | Kanban Box '(CRUD)' | 50% | UI, Logic
11 | Production | Material Return | Material Return '(CRUD)' | 0%
12 | Quality | Material Request | Material Request '(CRUD)' | 0%
13 | Quality | Return to warehouse | Return to warehouse '(CRUD)' | 0%
14 | Master | List Material | List Material '(CRUD)' | 100% | OK
15 | Master | BOM | BOM '(CRUD)' | 50% | Add Material's BOM, Search BOM,
Total |  |  |  | 45%