## Marco
# | Menu | SubMenu | Activity | Status | Notes
1 | Auth | Login | Manage user login (CREATE) | 100% | OK
1 | Admin | Dashboard |  | 0% | Belum tau mau diisi dengan apa
2 | Admin | Manage User | Manage User '(CRUD)' | 100%
3 | Admin | Manage Role | Manage Role '(CRUD)' | 10% | Baru hanya UI
4 | Admin | Manage Menu | Manage Menu '(CRUD)' | 100% | OK
5 | Admin | Manage SubMenu | Manage SubMenu '(CRUD)' | 25% | Baru Add
6 |  |  |  | 0%
7 |  |  |  | 0%
8 |  |  |  | 0%
9 |  |  |  | 0%
10 |  |  |  | 0%
11 |  |  |  | 0%
12 |  |  |  | 0%
13 |  |  |  | 0%
Total |  |  |  | 18.08%